# When does prototype build planning commence and what are key milestones?

Prototype build planning commences cicra 40 weeks before MRD. This activity is led by the PVO PBP teams. It is essential to capture the requirement for a prototype build (X1/FIS/VB/Rig/Labcar/Proto BIW) within the PVO workplan as far in advance of the MRD as possible. This will allow the PVO PBP teams and Whitley/ DC7 build teams to conduct capacity/ resource planning and flag up any concerns around supporting the prototype build in question.

Build planning preparation will require involvement from programmes/ engineering/ vehicle engineering/ product information/ marketing/ finance/ MP&L/ Build team/ PVO/ PVE.

For a major build the key milestones leading up to MRD are:

- 34 weeks to MRD – Frozen OXO

- 30 weeks to MRD – Frozen SDV

- 29- 23 weeks to MRD – Feature Coding/ Schedule Creation

- 22- 15 weeks to MRD – BoM Validation

- 14 - 13 weeks to MRD – MP&L Claim/ Condition BoM

- 12 weeks to MRD – Schedules Released

JLR-SPL-555055: PVO/PPBP - Engineer Training Pack v2.2 (sharepoint.com)

JLR-DTP-162211: Raising a PVO Workplan Change Request (sharepoint.com)

__________________________________________________________________________

Utterances:

- PVO

- Prototype

- X1

- FIS

- VB

- PBP

- DC7

- Labcar

- BIW

- Build Planning

- Prototype Vehicle Operation

- Donor

- Verification Build

- Functional Integration Simulator

- Ground Up