Key Drivers for SV Halo VPF Development?

SV Halo is usually one ‘Model Year’ later than the core programme. The MY stagger helps enable donor vehicle supply for X1 & FIS builds. SV Halo programmes aim to have an aligned launch phase with Core to maximise cost and keep within TFLE.

Design is not critical path compared to core as package/proportions are already understood. SV Halo underbody technical validation and development forms critical path.

The typical SV Halo VPF development process is:

- Commence with high level VPF scenarios

- Identify critical path activities, risks & opportunities

- Review VPF scenarios at Agile Planning Review (TPAT)

- Identify enablers & appetite to risk with key stakeholders

- Approve VPF at KO & commence P6 planning/metrics

- Baseline VPF at PS using P6 planning/metrics

- Transition to Planning Delivery team between KO to PS

__________________________________________________________________________

Utterances:

- SV

- Halo

- VPF

- Critical Path

- Pre KO

- TPAT

- Agile Planning Review

- Risks

- Opportunities

- P6

- KO

- Enablers

- Baseline VPF

- SV Planning

- Pre KO Planning